## 16-Week Milestones
Week | Timeline | Milestone | Objective | Key Tasks | Status | Owner | Notes
Week 1 | Sep 1 – Sep 7 | Own Website & Domain for The North One | Establish a professional online presence with the official website and domain. | Finalize website content; verify all pages and links; connect the domain; test desktop/mobile responsiveness; confirm contact details and social links. | Not Started
Week 2 | Sep 8 – Sep 14 | Social Media Setup & Establishment | Create and establish professional social media presence for The North One. | Create/optimize Instagram and LinkedIn; finalize bios and profile details; add website/contact information; prepare initial posts; maintain consistent branding. | Not Started
Week 3 | Sep 15 – Sep 21 | Creating Proper Packages & Prices for All Services | Create clear service packages and pricing that are easy for clients to understand. | List all services; group services into packages; define inclusions and deliverables; decide pricing; prepare package presentation/proposal; review internally. | Not Started
Week 4 | Sep 22 – Sep 28 | Pitching Clients | Start active client acquisition by presenting The North One's services to potential clients. | Identify potential clients; prepare pitch deck/proposal; contact prospects; schedule meetings; present services; record leads and follow-ups. | Not Started
Week 5 | Sep 29 – Oct 5 | Shooting Demo Videos | Create demo videos that clearly showcase The North One's capabilities and services. | Finalize video concepts; prepare scripts; shoot content; edit demo videos; add branding; create versions suitable for social media and client pitches. | Not Started
Week 6 | Oct 6 – Oct 12 | Finalising Clients | Convert active leads into confirmed clients and finalize project requirements. | Follow up with leads; discuss requirements; finalize scope and pricing; confirm deliverables; agree timelines; onboard selected clients. | Not Started
Week 7 | Oct 13 – Oct 19 | Working with Clients & Exploring New Services | Deliver client work while identifying opportunities to expand The North One's service offering. | Work on active projects; communicate with clients; track deliverables; research potential new services; identify client needs and market gaps. | Not Started
Week 8 | Oct 20 – Oct 26 | Working with Clients & Pitching to Other Clients | Continue client delivery while expanding the pipeline through new pitches. | Complete ongoing client tasks; collect feedback; identify new prospects; send proposals; conduct pitches; follow up with interested clients. | Not Started
Week 9 | Oct 27 – Nov 2 | Exploring New Services, Working with Clients & Pitching New Clients | Balance client delivery, new-service exploration and continued business development. | Deliver client projects; research and shortlist new services; test suitable ideas; identify prospects; pitch new clients; document feedback. | Not Started
Week 10 | Nov 3 – Nov 9 | Exploring New Clients & New Services | Expand the client pipeline and continue researching services that can strengthen the agency. | Research new client segments; build prospect list; contact prospects; study new service opportunities; compare requirements; shortlist services to develop. | Not Started
Week 11 | Nov 10 – Nov 16 | Exploring & Working on New Services | Move selected new service ideas from exploration toward practical development. | Define the selected service; research tools/resources; create workflow; develop a demo/prototype; test the service; collect internal feedback. | Not Started
Week 12 | Nov 17 – Nov 23 | Working on New Services | Develop and refine the selected new service so it is ready for client delivery. | Improve the workflow; finalize deliverables; create service materials; prepare demo content; test quality; define pricing/package structure. | Not Started
Week 13 | Nov 24 – Nov 30 | Adding the New Service | Officially add the new service to The North One's service portfolio. | Finalize service name and description; add it to website/social media; update packages; prepare promotional material; create client-facing demo/proposal. | Not Started
Week 14 | Dec 1 – Dec 7 | Client Exploration with All Services Including the New Service | Reach potential clients with the complete and expanded service portfolio. | Identify prospects; present existing and new services; send proposals; conduct meetings; highlight relevant packages; track responses and follow-ups. | Not Started
Week 15 | Dec 8 – Dec 14 | Client Pitching & Conversion with All Services | Convert qualified prospects into projects using the complete service offering. | Pitch targeted packages; negotiate scope and pricing; follow up with leads; close suitable projects; finalize agreements; plan onboarding. | Not Started
Week 16 | Dec 15 – Dec 21 | Client Acquisition, Retention & Service Validation | Strengthen the client base, validate the expanded services and prepare for the next growth phase. | Acquire new clients; maintain existing client relationships; collect feedback; evaluate new-service demand; review results; identify improvements and next steps. | Not Started

## Progress Summary
THE NORTH ONE — 16-WEEK MILESTONE TRACKER
Total Milestones | 16
Completed
In Progress
Not Started
On Hold
Overall Progress